## Sheet1
Start Date | Week | Status | Hours | Focus | Output
2026-02-02 | 1 | Done | 12 | Planning, tutor proposal, initial research | Proposal sent and notes
2026-02-09 | 2 | Done | 15 | Plan refinement, success criteria, literature shortlist and ethics draft | Plan, criteria ethics draft and sources list
2026-02-16 | 3 | Done | 10 | TMA01 Sections 1–2 writing, preparing PROMPT | First sections and PROMPT draft
2026-02-23 | 4 | Done | 16 | Ethics resubmission, finish TMA01 and update schedule | Ethics resubmitted and near-final TMA01
2026-03-02 | 5 | Done | 15 | Submit TMA01; begin design of MQTT contract and schema | Topic/payload specification and schema v1
2026-03-09 | 6 | Done | 10 | Research new material while waiting for the TMA01 results | Additional material for the literature review
2026-03-16 | 7 | Done | 14 | Expand literature on remote connectivity, MQTT reliability and persistence | Annotated source list and literature notes
2026-03-23 | 8 | Done | 12 | Refine project scope and define the literature-based stretch challenge | Revised scope and gap statement
2026-03-30 | 9 | Done | 13 | Draft gateway architecture and outage/recovery sequence diagrams | Architecture and recovery sequence drafts
2026-04-06 | 10 | Done | 10 | Design initial impairment test plan and tc/NetEm scenarios | Initial test plan and scenario table
2026-04-13 | 11 | Done | 11 | Update resources, lifecycle choice and project risk matrix | Risk matrix and revised planning section
2026-04-20 | 12 | Done | 16 | Rewrite literature review and project work sections for TMA02 | Revised Sections 2 and 3 draft
2026-04-27 | 13 | Done | 14 | Review and write Sections 4 and 5 for TMA02 | Revised Sections 4 and 5 draft
2026-05-04 | 14 | Done | 15 | Complete LSEPI, reflection, appendices and final TMA02 review | TMA02 completed and submitted
2026-05-11 | 15 | Done | 11 | Consolidate MQTT message schema, local broker and gateway component design | Updated message contract and component architecture
2026-05-18 | 16 | Done | 13 | Design SQLite WAL outbox, message states and idempotent duplicate control | Outbox schema and durable state model
2026-05-25 | 17 | Done | 12 | Validate tc/NetEm impairment tooling and record baseline and impaired results | Initial impairment evidence and documented limitations
2026-06-01 | 18 | Done | 10 | Review TMA03 requirements and plan the report structure and word allocation | TMA03 structure and section word count
2026-06-08 | 19 | Done | 14 | Revise project description, SMART objectives and comparison with existing solutions | Updated Section 1 and clearer project gap
2026-06-15 | 20 | Done | 15 | Rewrite the literature review, plan the PROMPT appendix and explain replay and retransmission | Revised Section 2 and stronger source comparison
2026-06-22 | 21 | Done | 12 | Update resources, risks, lifecycle comparison and Gantt chart | Revised Section 3 and updated planning evidence
2026-06-29 | 22 | Done | 15 | Refine the gateway architecture, SQLite state transitions and controlled recovery logic | Updated architecture and controlled recovery diagrams
2026-07-06 | 23 | Done | 16 | Rewrite Section 4, address tutor feedback and reduce Sections 1–4 to the word budget | Condensed Sections 1–4 while retaining technical evidence
2026-07-13 | 24 | Done | 12 | Complete Section 5, references and appendices, then submit TMA03 | TMA03 completed and submitted; implementation phase ready to begin
2026-07-15 | 25 | Done | 13 | Started the implementation from the TMA03 design: message contract, SQLite WAL outbox and local MQTT ingestion (this was almost ready at the time) | Validated message model, schema and durable local ingestion with automated tests
2026-07-20 | 26 | Done | 10 | Implement upstream QoS 1 publication, delivery-state transitions and the independent evaluation collector (schemas were ready) | Baseline upstream publication and collector evidence working; reconciliation workflow established
2026-08-27 | 27 | Done | 11 | Add persistent duplicate evidence and reconcile repeated and conflicting observations; I have to implement and resolve afterword some issues with the collector-only. | Payload conflicts recorded; duplicate-control evidence and tests completed
2026-08-03 | 28 | Done | 18 | Implement stale in_flight detection and recovery to retry_wait, including restart and state-transition tests | Stale-state recovery implemented and verified without incrementing attempt_count
2026-08-10 | 29 | Done | 17 | Implement controlled recovery with link-stability gating, QoS 1 health checks, bounded replay and per-stream ordering | Controlled recovery implemented with bounded batches, failure handling and recovery tests
2026-08-17 | 30 | Done | 15 | Prepare impairment-evaluation tooling and deploy the gateway physically on Raspberry Pi with upstream services on Windows | Physical Raspberry Pi evaluation environment established and preflight evidence collected
2026-08-24 | 31 | Done | 20 | Validate NetEm routing, correct the invalid same-host impairment topology, resolve collector/reconciliation problems and repeat preflight runs (Expend a lot of time testing) | Pi-to-Windows impaired path confirmed; unsuitable runs excluded and evidence workflow corrected
2026-08-31 | 32 | Done | 25 | Run formal baseline, degraded and outage evaluations; repeat or exclude invalid runs and analyse delivery, duplicates, backlog drain and storage | Evidence reconciled; excluded runs documented; final tables, graphs and EMA analysis in progress
2026-09-07 | 33 | Done | 40 | Working on the final document after have analysed all the results. Putting all the eviden togheter for the document | After along with working only in the EMA, I will need a few days to review it.
2026-09-13 | 34 | Done | 20 | Finished with the document, I have created a new template design and I am ready to finish it | I have completed the work, and I have bein removing unecessary documentation of the repository because it increased considerably